## MANAGEMENT RESPONSE AND ACTION PLAN MATRIX

Evaluation of IOM Accountability to Affected Populations

Name and function of the management response coordinator (MR coordinator): Sara M. Basha, Senior AAP Policy and Project Advisor, Protection and AAP Division, IOM Headquarters.

Date of publication: December 2024.

Overall comment on evaluation process (optional): The evaluation encountered obstacles during its conduction of technical and organizational nature, resulting in heightened methodological limitations. However, these did not affect the overall acceptability of its conclusion and recommendations.

Evaluation recommendation # 1: The AAP team should clarify that the scope and applicability of AAP extends beyond emergency response operations, reinforcing also the message on the mandatory nature of IN/285. This recommendation responds to findings suggesting that doubts persist regarding the mandatory nature of IN/285 and its applicability beyond emergency response operations, considering that the instruction focuses specifically on this type of intervention. To this end, a revision of the instruction or the release of other types of official statements specifically addressing these doubts should be considered.

Responsible unit(s): AAP Unit

Management response - accept/partially accept/reject: AAP unit accepts the recommendation. The mandatory nature of IN/285 and its applications beyond crisis response operations is fully understood and supported by the organization’s senior leadership. This commitment was further reinforced through the structural adjustment process in 2025, which led to the establishment of the Protection and AAP Division within DHRR. This new division brings together key areas of work including the Accountability to Affected Populations (AAP) Unit, Humanitarian Protection (including the GBV team), and the Gender and Diversity Coordination (GDC) Unit, with the aim of enhancing coherence and advancing the integration of protection and AAP principles across all programming contexts—not only humanitarian. While the revision of IN/285 is pending, the AAP unit has been working on several initiatives which focused on extending the scope of AAP beyond crisis settings. This includes organizing trainings targeting diverse programs under the operations pillar, initiating the development of a broader institution wide CFM toolkit, working on the development of a CFM database system which can be used by all IOM programs, etc. Furthermore, the team has proactively initiated inter-departmental discussions with the Division on Peace, Recovery and Solutions, exploring opportunities for integrating AAP into Community Based Planning (CBP) in countries in transition. Input from the ongoing initiative with CBP will be an important input in the revision process. Key actions: - Mobilize resources for onboarding a consultant to support revision of IN/285, develop an institutional strategy and a Theory of Change on AAP in coordination with relevant departments in HQ as well as colleagues in the field (2025). If resources are not secured for this action, the AAP Unit will proceed with a minimal revision of IN/285, focusing on expanding the AAP scope beyond crisis response operation. Nonetheless, the AAP unit will continue to look for resources to onboard a consultant/thematic expert to support revisions of the institutional guidance and develop an AAP strategy and TOC for the organization. - Organize webinars with CO and RO staff on the extended scope of AAP (2025/2026).

Implementation monitoring status - discarded/open/completed: (Time 2) Complete this field when following up for the first time on the management response and key actions. Indicate if the implementation of the recommendation is discarded, open or completed. “Discarded” should be used if the recommendation is no longer relevant or applicable. E.g., if the recommendation suggests preparing a second phase of the project with the donor, which is however confirmed as not possible by the donor in the meantime, then the recommendation can be discarded. The “completed” option should be used if all actions are implemented, or at least part of the key actions are implemented and there are no further plans to implement the remaining key actions for this recommendation. The “Open” option should be used if still relevant but not yet implemented or in process. Comments on implementation status: (Time 2) Add brief explanations and/or description of the status of actions taken. For instance, if partially completed, or no longer applicable; if insufficient support is received to implement the recommendation; if some actions go beyond the sphere of the responsible unit(s), and therefore need to be reassigned; if there is any outstanding issue or delay in the implementation of the recommendation. These fields are to be completed by the responsible unit(s) and coordinated by the MR coordinator. Complete the field when following up and monitoring the implementation of the key action described in the previous box.

Final implementation monitoring status - discarded/open/completed: (Time 3) Specify the final status of the implementation of the key actions according to the definitions provided above. The final status section does not need to be completed if all recommendations have been completed and closed at Time-2 above. Final comments on implementation status: (Time 3) Use the field to provide further clarifications on the final implementation monitoring status. If a recommendation is still open after 15 months, considerations will be given on the status related to the closure of the MR process. The ’Time-3’ fields are to be completed by the Responsible Unit(s) and coordinated by the MR coordinator as the second and final round of monitoring between 12 and 15 months after the publication of the evaluation report.

Evaluation recommendation # 2: The AAP team should develop an operational medium- to longer-term strategy for AAP, to be negotiated at the highest leadership level, with a three-year plan connected to a funding strategy. This recommendation considers findings on the uneven support for AAP among IOM senior management, placing emphasis on the need to have the strategy endorsed at the level of deputy director generals, or even directly by the Director General. The resulting strategy should also be usable as a fundraising tool to attract more resources towards AAP, while also mobilizing core funding to show the Organization’s institutional commitment to AAP.

Responsible unit(s): AAP Unit

Management response - accept/partially accept/reject: The AAP Unit accepts the recommendation. Developing an institution-wide AAP strategy is a key objective for the unit. To fulfill this commitment and its operationalization, the team will engage in fundraising efforts through existing broader operational programmes, initiatives and/or solicit support from donors. Key actions: - Develop an organizational strategy and a Theory of Change on AAP (2025 subject to availability of funds). This activity will be implemented in conjunction with key actions proposed in recommendations 1 and 3.

Implementation monitoring status - discarded/open/completed: (Time 2) Comments on implementation status: (Time 2)

Final implementation monitoring status - discarded/open/completed: (Time 3) Final comments on implementation status: (Time 3)

Evaluation recommendation # 3: In conjunction with Recommendation 2 above, the AAP team should develop a theory of change and a dedicated monitoring and evaluation framework for AAP. A more structured strategic approach to AAP will require a dedicated and robust framework for its effective monitoring. A new dedicated framework can build from the current existing framework, but will need to feature additional indicators (formulated also on the basis of the findings of this evaluation) and, where necessary, improve the formulation of some of the existing outcome indicators. The new framework must not be limited to monitoring, but must also include an evaluation plan that can, at a minimum, include reviews or evaluations at regular intervals, or evaluative exercises focused on specific aspects of AAP or initiatives, considering also impact assessments.

Responsible unit(s): AAP Unit

Management response - accept/partially accept/reject: AAP unit accepts the recommendation. Since 2024, significant progress has been made in strengthening results-based monitoring for AAP across the organization. This includes the development and initial implementation of institutional AAP-specific indicators embedded in the Strategic Results Framework (SRF), particularly under Strategic Objective 1 (Saving lives and protecting people on the move) and Cross-Cutting Priorities 1 (Integrity, Transparency and Accountability) and 3 (Protection-centred). These indicators are designed to measure both institutional performance and the organization’s broader commitment to AAP. Regional efforts have been implemented to monitor the integration of IOM's AAP framework in country operations (e.g., regional monitoring for Ukraine response, CFM evaluation for an EU funded flagship project “Migrant Protection, Return and Reintegration (MPRR) which is implemented in 15 Sub-Saharan African countries). However, these efforts need to be consolidated and further developed into an M&E framework for AAP. Current monitoring efforts tend to focus more on activities and outputs rather than outcomes or impact, and there is no structured plan for periodic evaluation exercises focused on AAP performance or impact. The M&E framework should include a revision and expansion of the current indicators, to include non-crisis settings. It should also ensure better coverage of qualitative data collection through evaluation activities, including impact evaluation (e.g., outcome harvesting through meaningful participation). Key actions: - Conduct additional regional monitoring exercises to test the existing M&E assessments (2025) - Develop AAP M&E framework (2026 subject to availability of funds)

Implementation monitoring status - discarded/open/completed: (Time 2) Comments on implementation status: (Time 2)

Final implementation monitoring status - discarded/open/completed: (Time 3) Final comments on implementation status: (Time 3)

Evaluation recommendation # 4: The senior management and the Protection Division should strengthen central AAP functions, ensuring that the size of the AAP unit in IOM Headquarters becomes adequate for meeting AAP strategic objectives and that there is capacity to proactively support country offices in structuring their approach to AAP implementation. For the follow-up to this recommendation, the following activity should be considered: - Increase staff resources in regional offices, establishing AAP-dedicated positions or designating focal persons with both technical knowledge and time capacity, ensuring these have a clear mandate to undertake AAP tasks effectively and efficiently, and that technical reporting lines to AAP officers in IOM Headquarters are established.

Responsible unit(s): Deputy Director General for Operations and Protection and AAP Division

Management response - accept/partially accept/reject: The recommendation is relevant and accepted. In January 2024, IOM's senior management decided to cover a senior AAP staff position from the core budget. This decision indicated the significance of the AAP unit's work and the need for consistent leadership within the team. In 2025, an additional AAP position was also core-funded, further strengthening the unit’s capacity. These roles, alongside staff supported through the flexible funding mechanism, have helped stabilize the unit and enabled it to engage in longer-term planning. As of 2025, the AAP Unit became part of the newly established Protection and AAP Division within the Department of Humanitarian Response and Recovery.. The AAP Unit works closely and across the Operations Pillar, to place the rights, dignity and well-being of migrants and displaced persons—regardless of their legal status—at the centre of IOM’s operations This restructuring reflects the Organization’s commitment to AAP and Protection as cross-cutting institutional priorities under the Operations Pillar, supporting coherence and integration across all areas of programming. AAP capacity in regional offices is currently unavailable due to funding constraints. The central AAP unit at Headquarters will continue to directly support country offices and organize trainings for COs and ROs until more funds are available. Senior leadership is dedicated to ensuring that country offices understand AAP is mandatory for IOM operations. The training module developed under IASC is integrated into leadership training and will be rolled out in 2025 through regional trainings, promoting accountability and incorporating community insights from the planning stage. Key actions: - In coordination with the Regional Support and Coordination Unit (RSCU) in the Chief of Staff Office and the Department of Human Resources (DHR), aim to make the online AAP training mandatory for all staff, including COMs and RDs (2025 - 2028) - Explore ways to fund raise and deploy AAP expertise in regional offices - including through strengthening partnership with Standby Partners (SBPs) 2025 – 2028) - Central AAP Unit will organize AAP thematic training for RTSs (2025 – 2028)

Implementation monitoring status - discarded/open/completed: (Time 2) Comments on implementation status: (Time 2)

Final implementation monitoring status - discarded/open/completed: (Time 3) Final comments on implementation status: (Time 3)

Evaluation recommendation # 5: The AAP team should support country offices in developing office-wide approaches to AAP implementation and funding, reducing fragmentation. This recommendation should be based on known cases of office-wide approaches to AAP, such as IOM Ethiopia (Case study 1), where AAP functions are centralized in a specific unit, a network of AAP focal persons has been established, and funding for AAP activities is regularly included in and taken from different initiatives proportional to their budget. Central AAP functions should establish minimum standards for operating AAP at the country level and should provide different models for the funding and centralization of AAP functions, taking into account different country office sizes, specializations and operational contexts. For the follow-up to this recommendation, the following activities should be considered: - Develop specific guidance on AAP system development in country offices, including funding methodologies. - Establish a fund for supporting select country offices to cover the start-up costs of integrated, office-wide AAP systems. Select recipients of support through open competition.

Responsible unit(s): AAP Unit

Management response - accept/partially accept/reject: The management team accepts the recommendation. Expand the scope of AAP is essential for guiding country offices to adopt a mission-wide approach. This will make AAP a priority across all programs and ensure adequate resources are allocated. Learning from country offices with experience in integrating AAP and allocating proper resources can serve as a good starting point. The Central AAP team will continue to support COs develop mission-wide AAP strategies. These strategies are linked to a minimum AAP standard and integrated into their fund-raising strategies. Initiatives have already started with a few IOM missions operating in non-crisis settings. In coordination with the Regional Support and Coordination Office, the Central AAP team will engage the ROs and COs to ensure AAP principles are effectively integrated into regional and country level operational strategies. Advocating adequate resources to support AAP initiatives is key. Implementing a robust project management cycle and advocating for a dedicated AAP budget especially in flagship initiatives, regional projects/programs and appeals, are some of the important steps to take. Key actions: - In coordination with the RSCU in the Chief of Staff's office and DHR, advocate for AAP training to become mandatory for COMs, RDs, DRDs and other senior leadership teams (2025 – 2028) - Integrate AAP into project development handbook and advocate to make it mandatory for all IOM programs and operations – project development, review and endorsement (2025 - 2026) - Allocate sufficient funds to support AAP initiatives. (2025 – 2028 subject to availability of funds) - Continue to support COs to develop AAP strategies. (2025 – 2028) - Provide support to ROs and COs in integrating AAP into program strategies and fundraising mechanisms (2025 – 2028). - Disseminate good practices among CO and ROs on mainstreaming AAP – including fund raising for AAP, M&E practices around AAP, human stories from affected communities on the impact of CFM, meaningful participation, access to information and transparency, etc. (2025 – 2028)

Implementation monitoring status - discarded/open/completed: (Time 2) Comments on implementation status: (Time 2)

Final implementation monitoring status - discarded/open/completed: (Time 3) Final comments on implementation status: (Time 3)

Evaluation recommendation # 6: The Protection Division and the AAP team should increase the visibility of AAP activities, both internally and externally, on the basis of a clear visibility and knowledge management plan. The desk review of AAP documentation clearly indicated that an insufficient amount of “visibility” material, including case studies and AAP best practice documentation, has been produced to document AAP activities and their influence on the work of IOM. It is key that efforts on AAP visibility are formalized in a dedicated plan, formulated by the AAP central unit in coordination with communication specialists, and that country offices are provided with guidance, tools and support on AAP best practices around documentation and visibility. Increasing the visibility of AAP activities should not be limited to producing dedicated material; as well, general communications on IOM interventions should highlight their AAP components and results. For the follow-up to this recommendation, the following activities should be considered: - Conduct a comprehensive mapping of AAP activities and approaches, on which the identification of good practices can be based. - Establish regular dissemination channels on AAP (such as newsletters, blogs and webinar series), with the specific intent of giving visibility to good practice and innovative initiatives. - Promote the publication and dissemination of case studies on AAP, building on communities of practice and collaboration with other thematic and programme areas. - Use communications to strengthen incentives for engagement in AAP, including prizes given to best initiatives, solutions and achievements. - Strengthen current knowledge management practice in AAP.

Responsible unit(s): AAP Unit; Protection and AAP Division

Management response - accept/partially accept/reject: Management accepts the recommendation. Documenting best practices from AAP programming and country offices is an important means of giving visibility to the organizations work on AAP and support country offices to learn from each other and have better understanding of the work other COs are leading and/or supporting. Central AAP team will also strengthen the AAP community of practices through regular engagements with AAP focal points; and organize thematic webinars with RO and COs to further strengthen visibility and awareness of AAP implementation within the organization and beyond. IOM country offices will be encouraged and invited to present at interagency AAP online meetings and webinars on AAP and related thematic areas. Key actions: - Strengthen and revive the existing AAP community of practice in IOM 2025 - 2028 - Plan for and organize thematic webinars on AAP and related topics 2025 - 2028. - Facilitate and create opportunity for COs to take part in and present on their work at interagency (2025 – 2028)

Implementation monitoring status - discarded/open/completed: (Time 2) Comments on implementation status: (Time 2)

Final implementation monitoring status - discarded/open/completed: (Time 3) Final comments on implementation status: (Time 3)

Evaluation recommendation # 7: The AAP team should increase training opportunities and update capacity-building material with increased focus on practical AAP implementation and including standard tools and templates, which will have been developed in consultation with relevant field offices, partners and community of practice members. Informants overwhelmingly indicated that more practical guidance on AAP is needed. Such guidance could include standard CFM SOPs, template feedback forms, off-the-shelf CFM management systems and CFM data analysis dashboards, all of which should be easily adapted to and deployed in field contexts. Training material and capacity-building resources should also be expanded accordingly and should place renewed focus on practical AAP implementation. The training supply should also be expanded, as demand is currently not fully met. For the follow-up to this recommendation, the following activities should be considered: - Develop practical guidance material (such as a template and guidance for AAP data-sharing agreements, CFM forms, etc.) based on the requests of field-level AAP focal persons and involving the AAP community of practice. - Critically review current training methodology and identify ways in which training effectiveness can be enhanced, and in which the notions acquired can be put to practical use. This may include on-the-job training arrangements, training follow-ups, and peer review and engagement. - Include AAP-related material in the current revision of the IOM Project Handbook to bridge the gap between policy and practice. - Develop and conduct an AAP training-of-trainer initiative.

Responsible unit(s): AAP Unit

Management response - accept/partially accept/reject: AAP Unit accepts the recommendation. The AAP team is developing a CFM toolkit with practical guidance to support CFM implementation. It will include templates for SOPs, feedback collection forms, standard categorization, M&E frameworks, and CFM management procedures. The goal is to strengthen capacity and institutionalize good practices across programming. In 2024, a new three-day AAP training curriculum for Country and Regional Offices was finalized and piloted in Jordan and selected countries in Southern and Eastern Africa region, receiving very positive feedback on its methodology, materials, organization, and interactivity. If funding permits, the implementation of this training will continue. An updated AAP chapter for the IOM Project Handbook has been developed and will be published when the Handbook is made available. Meanwhile, the team is exploring options to share the content as a standalone resource to support AAP integration in project development, implementation, evaluation, and donor reporting, where demand for evidence of AAP is growing. The 2025 workplan includes developing an AAP Training of Trainers (ToT) package, pending available funding. Key actions: - Finalize the development of a CFM toolkit and translate into Arabic, French and Spanish (2025/2026 subject to availability of funds) - Organize webinar/trainings for COs and ROs (2025 – 2028) - Finalize a tailored AAP specific project development handbook (2025) - Develop AAP TOT training package (2025 – 2026 subject to availability of funds)

Implementation monitoring status - discarded/open/completed: (Time 2) Comments on implementation status: (Time 2)

Final implementation monitoring status - discarded/open/completed: (Time 3) Final comments on implementation status: (Time 3)

Evaluation recommendation # 8: The AAP team should enhance and standardize CFM systems used in IOM through the following actions: - Map existing CFM systems. - Conduct a comprehensive assessment of all CFM systems currently in use within IOM. - Identify overlaps, gaps and areas for improvement in existing mechanisms. - Establish minimum standards and ensure compliance. - Define clear minimum standards for CFM systems to ensure consistency, efficiency and accessibility. - Implement measures to ensure that all mapped CFMs align with these standards. - Develop and disseminate CFM-specific materials. - Create guidance documents, training materials and communication resources to support the effective implementation of CFMs. - Ensure dissemination across all relevant teams and offices. - Move towards standardization and integration. - Work towards harmonizing CFM systems across IOM to ensure uniformity in processes and reporting. - Facilitate the integration of CFMs into broader corporate systems for streamlined data collection and analysis. This recommendation relates to the many findings regarding CFMs in this evaluation, and in particular to how CFM development and management processes are being undertaken in autonomy by different offices or departments within IOM, resulting in duplication of effort and missed opportunities for efficiency and synergy. Central AAP functions are therefore recommended to control and regulate CFM-related processes and outputs more actively. New guidance on developing and managing CFMs should cover both technological and organizational aspects, with the former focusing on minimum standards and compliance, and the latter promoting the development of office-wide CFM systems with clear processes, roles and responsibilities for the various functions available in the office. Noting also how CFM development has happened outside of institutional system development and management processes, after having established minimum standards, in particular on data protection, cybersecurity and data utilization (as the prevalent perception of informants was that not all CFM data are analysed and used), IOM should move towards the institutionalization of the more promising CFM systems available within IOM and beyond, possibly through a transparent, open selection process.

Responsible unit(s): AAP Unit

Management response - accept/partially accept/reject: AAP Unit accepts the recommendation The updated guidance on CFM, as part of the CFM toolkit currently under development, will define clear minimum standards for CFM to ensure consistency in feedback management and interoperability of systems. This will be particularly supported by a unified taxonomy that promotes institution-wide categorization of feedback, integrating inter-agency standards to better aggregate feedback across programming and enhance collaboration with other UN agencies and beyond. These standards will also ensure compliance with existing IOM policies and facilitate the integration of data from various CFM systems, enabling improved aggregation and trend identification at national, regional, and global levels. The CFM toolkit will serve as a comprehensive resource, combining guidance, standards, and practical tools to support the effective implementation of CFMs. The vision is for the guidance to progressively become mandatory, across IOM to manage CFM and categorize feedback. To ensure this, support from Senior Leadership will be needed. It should be noted that the CFM toolkit, its guidance and tools, have undergone two consultations with different colleagues across Headquarters, regional offices and focal points from field contexts. Additionally, AAP is developing CFM Connect, a unified system for CFM management that could serve as a corporate system, which integrates and builds on the same technology as other IOM internal platforms, including We Are All In and OIOintake@iom.int. This system will incorporate the updated CFM guidance and taxonomy, enabling feedback aggregation and early-warning trend identification, even when different systems are used by COs and ROs. Key actions: - Finalize the development of a CFM toolkit and translate into Arabic, French and Spanish (2025 – 2026 subject to availability of funds) - Finalize the development of CFM Connect system (2025)

Implementation monitoring status - discarded/open/completed: (Time 2) Comments on implementation status: (Time 2)

Final implementation monitoring status - discarded/open/completed: (Time 3) Final comments on implementation status: (Time 3)

Evaluation recommendation # 9: IOM more broadly, and the AAP team more specifically, should continue the collaboration and engagement on collective accountability, actively participating in coordination structures on AAP, such as IASC-promoted initiatives or initiatives developed in other inter-agency coordination spaces, both at the global and country level. To follow up this specific recommendation, the following activities should be implemented: - Disseminate best practices on collective accountability and inter-agency coordination, including on the implementation of joint projects such as inter-agency CFMs or other similar initiatives, and conduct specific training courses on this matter. - Ensure AAP focal points or dedicated staff have formalized inter-agency tasks in their job descriptions and their terms of reference, and that AAP coordination is part of the overall objectives of designated AAP roles. - Include AAP resources (staff capacity and funding) to allow for active IOM participation in inter-agency spaces, including co-leading AAP working groups and taskforces when relevant. - Include collective AAP contributions as a key metric of a revised theory of change and monitoring framework for AAP (linked to Recommendation 3). - Disseminate the IOM-led inter-agency leadership training on AAP to all IOM senior management. Showcase successful experiences of collective accountability within IOM (for example, Ethiopia and Response for Venezuela).

Responsible unit(s): AAP Unit

Management response – accept/partially accept/reject: AAP Unit accepts the recommendation. IOM continues to actively collaborate and engage in interagency discussions on AAP and collective accountability. Up until 30th June, 2024, IOM was an active member of the IASC TF 2 on AAP (until the TF was abolished). IOM continued to take part in an ad-hoc AAP interagency coordination meetings initiated by OCHA. IOM lead and supported the development of an interagency training module on collective AAP. This process involved establishing an active steering committee with key humanitarian actors from both UN and non-UN agencies. The training modules are intended for senior leadership and technical staff of humanitarian actors IOM is an active member of the CDAC network, a global alliance that provides affected communities with access to safe and trustworthy information during crisis. IOM in collaboration with OCHA is coordinating interagency AAP reporting to improve tracking of collective AAP implementation across HNRPs and reporting for FCDOs business case. Key actions: - Disseminate collective AAP senior leadership training modules with IOM missions, regional offices and amongst humanitarian actors in coordination with the Regional Support and Coordination Office (2025 – 2028) - Strengthen engagement with interagency AAP working groups (2025 – 2028). - Continue collaborating with OCHA on the joint reporting for FCDOs business case (2025 – 2028) - Establish a community of practice in support of IOM missions leading/co-leading interagency AAP work (2025 – 2028)

Implementation monitoring status - discarded/open/completed: (Time 2) Comments on implementation status: (Time 2)

Final implementation monitoring status - discarded/open/completed: (Time 3) Final comments on implementation status: (Time 3)

Focal persons are intended to be staffers not fully dedicated to working on AAP, but rather staffers who have AAP responsibilities alongside other responsibilities.